## Sheet1
CINEMA MANAGEMENT ESTIMATION
Epic/Features | Product Backlog Items | Task/ User Stories | Estimation(man/days) |  |  |  | Note
|  |  | DEV | Unit Test | UI/UX | QA
Login | Login | Login to system | 3 | 0.5 | 0.9 | 0.7
Account management | Search user info | Search by position/ name | 2 | 0.5 | 0.5 | 0.5
| Add user info |  | 2 | 0.5 | 0.6 | 0.6
| Edit user info |  | 3 | 0.6 | 0.6 | 0.6
| Delete user info |  | 3 | 0.4 | 0.7 | 0.5
Movie management | Search movie | Search by movie's name | 4 | 0.5 | 0.8 | 0.6
| Add movie |  | 4 | 0.5 | 0.7 | 0.6
| Edit movie | Edit based on movie's name | 2 | 0.9 | 0.9 | 0.9
| Delete movie | Delete based on movie's name | 2 | 0.6 | 0.9 | 0.8
Showtime management | Search movie's showtime | Search by movie's name/ room/ days/ time | 2 | 0.5 | 0.5 | 0.5
| Add showtime | Add based on movie's name/ room | 2 | 0.5 | 0.8 | 0.7
| Edit showtime | Edit based on movie's name/ room | 1 | 0.5 | 0.5 | 0.5
| Delete showtime | Delete based on movie's name/ room | 1 | 0.8 | 0.8 | 0.8
Booking Tickets | Search movie | Search based on days, on time/ movie | 2 | 0.9 | 0.9 | 0.9
| Search seat | Search based on position/number of seat | 2 | 0.5 | 0.5 | 0.5
| Search service | Search based on your favourites/ number of packeging | 3 | 0.5 | 0.7 | 0.6
| Search time | Search based on days, on time/ movie | 1 | 0.6 | 0.6 | 0.6
Cancel Booking Tickets | Searchs for the cinema room | Search based on room | 2 | 0.6 | 0.8 | 0.7
| Searchs for the movie | Search based on movie name | 2 | 0.6 | 0.8 | 0.7
| Searchs for the showtime | Search based on showtime | 2 | 0.8 | 0.8 | 0.8
| Searchs for the seat to be canceled | Search based on seat number | 2 | 0.6 | 0.6 | 0.6
Services | Searchs service | Search based on type/ number of services | 3 | 0.4 | 0.5 | 0.5
Payment | Pay money | Pay by cash / credit card | 2 | 0.7 | 0.5 | 0.6
Report | View report | View by days/ months/years/movies | 5 | 0.4 | 0.5 | 0.5
Total |  |  | 57 | 13.9 | 16.4 | 15.3